SimplerToday AI

Migration Work Plan — AWS and Azure

Full delivery plan for moving the AI service to Amazon Web Services or Microsoft Azure, with model portability — tasks, timeline, team, cost, risks and acceptance

| Item | Detail |
| --- | --- |
| Document | Migration work plan — prepared for client review |
| Service in scope | SimplerToday AI service (the AI worker that connects to the application backend) |
| Codebase | 115 modules · ~71,700 lines of Python |
| Paths | Path A — Amazon Web Services (EC2) · Path B — Microsoft Azure |
| Delivery | Phase 1 in 4 weeks with three engineers; phase 2 in 2–3 weeks after cutover |
| Version / date | v4.0 · 30 September 2026 |
| Status | Draft for discussion — cost figures are indicative and must be confirmed before contract |

Contents

Right-click the table above and choose Update Field if page numbers do not appear.

# 1. Executive summary

SimplerToday AI will move fully onto one of two clouds — Amazon Web Services or Microsoft Azure — with every service it depends on (compute, storage, OCR, transcription, search, language models and embeddings) running on that cloud. At the same time the service gains model portability: each product feature can use a different AI provider and model, chosen by configuration.

Both paths follow the same structure: a 4-week phase 1 that ends in a production cutover, delivered by a team of three engineers, and a short phase 2 that completes the remaining capabilities and full quality parity.

## 1.1 The two paths at a glance

|  | Path A — AWS (EC2) | Path B — Azure |
| --- | --- | --- |
| Phase 1 effort | 45–46 engineer-days | 45–46 engineer-days |
| Phase 1 calendar | 4 weeks | 4 weeks |
| Phase 1 | 15–21 days · 2–3 weeks | 11–15 days · 2–3 weeks |
| Web grounding for case law | Built in phase 2 | Native (Bing) in phase 1 |
| Download links | Redirect endpoint required | Works as today (SAS) |
| Run cost / month (economy → flagship) | ≈ $1,510 – $3,690 | ≈ $1,540 – $2,460 |
| Run cost / month — mixed models (recommended) | ≈ $1,960 – $2,640 | ≈ $1,815 |

For reference, the same workload on Google Cloud (Gemini via Vertex AI) runs at about $827 a month with the mixed model profile (≈ $584 economy, ≈ $1,394 flagship). The full three-way comparison is in section 6.2.

AWS ranges depend on the legal-search engine: self-managed OpenSearch, built in phase 1 (lower), or Kendra if query volume later justifies it (higher). Indicative USD list prices, Mumbai region.

# 2. Scope

## 2.1 In scope

- The SimplerToday AI service: receives workspace and chat events from the application backend, processes evidence, and returns the ten intelligence panels and chat replies.

- Integration of the existing model portability layer.

- Migration of compute, storage, OCR, transcription, legal search, web grounding, language models and embeddings to the chosen cloud.

- Data migration: object storage, the vector store and stored storage references.

- Quality proof, regression testing, cutover, rollback and handover.

# 3. Model portability integration (both paths)

The portability layer already exists and is integrated in 4–5 days. It is the first task on either path (A-01 / Z-01).

## 3.1 Approach

The service's existing model client keeps its methods — generate, long-form generate, grounded generate, chat and embed — and each one is re-implemented on top of the portability layer. Every feature keeps calling the same methods, so no feature code changes, and switching back is a configuration change.

## 3.2 Tasks

| Task | Days |
| --- | --- |
| Re-point the client methods at the layer (JSON output, long answers, chat, grounding, embeddings); keep error handling identical | 1.5–2 |
| Per-feature model selection — each feature tagged once at the handler level, the same way cost tracking already scopes work | 0.5–1 |
| Move the five direct SDK calls onto the client; embedding size check with per-model collections; per-model pricing | 1 |
| Tests — existing offline verification scripts plus a smoke run on the target cloud's model | 1 |
| Total | 4–5 |

## 3.3 What the layer must already provide

The 4–5 day figure holds if the layer already supports the following; each missing item adds about half a day to a day.

- Structured (JSON-only) output.

- Continuing an answer when the model stops early.

- Web-search grounding, or a clear "not supported" signal so case laws fall back to direct lookup.

- Token usage reporting in a common shape.

- Per-provider safety settings.

- Request timeouts and errors reported in one common shape.

## 3.4 Acceptance

- With the default configuration every panel and chat reply behaves as before; existing verification scripts pass.

- Any feature can be switched to the target cloud's model by configuration alone and returns valid output.

- Every response reports usage and price for the model that actually served it.

# 4. Work plan — Amazon Web Services (EC2)

Everything needed to run SimplerToday AI fully on AWS. Phase 1 delivers a production cutover in 4 weeks; phase 2 completes the remaining capabilities and full quality parity.

## 4.1 Service mapping

| Capability | AWS service | Notes |
| --- | --- | --- |
| Always-on AI service | EC2 instance running Docker; Auto Scaling group min = max = 1 for automatic recovery | Single instance only — one connection to the backend |
| Vector store | Qdrant on EC2 with an EBS volume (or Qdrant Cloud) | Snapshot and restore verified |
| Cache | ElastiCache for Redis (small) | Provisioned for continuity |
| Draft documents, templates, audio staging | S3, plus a small redirect endpoint for download links | S3 links expire after 7 days at most (R-A1) |
| OCR for scanned evidence | Amazon Textract | Benchmark on Indian court filings |
| Audio transcription + speaker separation | Amazon Transcribe | Benchmark Hindi–English audio |
| Language model | Amazon Bedrock — Claude (Opus tier for reasoning panels, Sonnet tier for the rest) | Through the portability layer |
| Embedding model | Amazon Titan Text Embeddings v2 (1,024-dim) | Vector store re-built from stored text |
| Web grounding for case law | Built from a search API + retrieval | Phase 2 — case laws use direct Indian Kanoon lookup meanwhile |
| Legal search fallback | Crawler + self-managed OpenSearch (Kendra optional at high query volume) | Phase 1 |
| Secrets and identity | Secrets Manager + IAM instance role | Old key files rotated and revoked |
| Logs, metrics, alarms, patching | CloudWatch (agent on EC2) + Systems Manager patching | OS ownership on EC2 (R-A3) |

## 4.2 Work breakdown — phase 1

| ID | Task | Owner | Days | Depends on |
| --- | --- | --- | --- | --- |
| A-01 | Portability integration — existing client methods re-pointed at the portability layer; per-feature model selection; five direct SDK calls moved; embedding size check; per-model pricing; tests | E1 | 4–5 | — |
| A-02 | AWS account, VPC, private subnets, NAT gateway with Elastic IP (static outbound address), budget alarms | E2 | 2 | Client: account |
| A-03 | EC2 launch template and machine image with Docker, ffmpeg and poppler; ECR registry; CI pipeline; Auto Scaling group of one; Systems Manager patch baseline | E2 | 3 | A-02 |
| A-04 | Qdrant on EC2 with EBS volume; snapshot, restore and verify; ElastiCache | E2 | 2 | A-02 |
| A-05 | Secrets Manager, IAM instance role; rotate and revoke existing key files | E2 | 2 | A-02 |
| A-06 | CloudWatch logs, metrics and alarms (socket disconnect, restarts); audit-log retention | E2 | 1 | A-03 |
| A-07 | Data migration to S3; backfill stored storage references in cached templates | E2 | 2 | A-08 |
| A-08 | S3 storage adapter and download-link redirect endpoint (agreed with backend team) | E3 | 3 | Backend sign-off |
| A-09 | Textract OCR adapter; flatten output to the text the pipeline expects; benchmark | E3 | 2 | Sample evidence |
| A-10 | Transcribe adapter with speaker separation; reproduce the [MM:SS] Speaker A: format; Hindi–English test | E3 | 4 | Sample evidence |
| A-11 | Titan embeddings; re-embed the vector store from stored text; retrieval-quality check | E1 | 1 | A-01, A-04 |
| A-12 | Golden set (10 anonymised cases with lawyer-approved outputs) and automated scorer | E3 | 3 | Client: cases |
| A-13 | Prompt tuning on Claude for all ten panels and chat until output is valid and meets the golden-set threshold; remaining polish continues in phase 2 | E1 + E3 | 7 | A-01, A-12 |
| A-14 | Bedrock Guardrails / safety posture on real evidence; cost tracking for Textract, Transcribe and Bedrock units | E1 | 2 | A-01 |
| A-15 | End-to-end regression on staging, parallel run, cutover, rollback rehearsal, runbooks, handover | All | 4 | All above |
| A-16 | Legal search fallback — crawler indexing Indian Kanoon into a self-managed OpenSearch index; query adapter returning passages and source links | E2 | 3 | A-02 |
|  | Phase 1 total |  | 45–46 |  |

E1 = AI engineer · E2 = cloud / DevOps engineer · E3 = backend & QA engineer (section 7).

## 4.3 Week-by-week plan — phase 1

| Week | E1 — AI engineer | E2 — cloud / DevOps | E3 — backend & QA |
| --- | --- | --- | --- |
| Week 1 | A-01 portability integration; service runs through the layer with no behaviour change. Request Bedrock model access and quotas. | A-02 foundation; A-03 machine image and CI started; A-05 secrets and key rotation. | A-08 S3 adapter and redirect endpoint; agree link change with backend team; start A-12 golden set. |
| Week 2 | Bedrock profiles live in the layer; A-11 embeddings and re-embed dry run; A-13 tuning starts (strategy, analysis report). | A-03 complete; A-04 Qdrant and cache; A-06 observability; A-07 data migration to staging. | A-09 Textract; A-10 Transcribe; A-12 golden set complete. |
| Week 3 | A-13 tuning remaining panels and chat; A-14 Guardrails and cost tracking. | A-16 legal search (crawler + OpenSearch); full staging deployment end to end; alarms; draft runbook. | A-13 tuning support (dates, parties, laws, drafting); golden-set scoring; OCR / transcription benchmark on real evidence. |
| Week 4 | Fixes from regression; final golden-set score. | Parallel run; IP allowlisting; cutover; rollback rehearsal. | A-15 full regression across every event, panel and file type; handover. |

## 4.4 Milestones and gates

| Gate | When | Pass criteria |
| --- | --- | --- |
| G0 · Start | Day 1–3 | AWS account with admin rights, model access requested, staging backend available, sample evidence and 10 golden-set cases received |
| G1 · Layer in place | End of week 1 | Service runs through the portability layer with no behaviour change; existing offline verification scripts pass; foundation network and secrets ready |
| G2 · Target reachable | End of week 2 | AWS models reachable through the layer; data migrated to staging; golden set and scorer ready |
| G3 · Staging complete | End of week 3 | All panels and chat return valid output on the target model; golden-set score at or above threshold; legal search fallback returns Indian Kanoon results; staging end-to-end run clean |
| G4 · Go / no-go | Week 4 | Regression passed, rollback rehearsed, backend team sign-off on the cutover window |

## 4.5 Phase 2 — after cutover

| ID | Task | Days |
| --- | --- | --- |
| P2-A1 | Web grounding for case law — search API + retrieval | 4–6 |
| P2-A2 | Golden set extended to 25–30 cases; prompt polish to full parity | 11–15 |
|  | Phase 2 total | 15–21 |

Phase 2 runs over 2–3 weeks with 1–2 engineers.

## 4.6 Running cost

### Fixed monthly infrastructure

| Line item | AWS |
| --- | --- |
| Application server, 2 vCPU / 8 GB, always on | $75–85 (EC2 on-demand + 30 GB EBS) |
| Qdrant, 2 vCPU / 8 GB + 100 GB disk | $85–100 (EC2 + EBS) |
| Redis cache, small | $25–30 |
| Object storage, 500 GB | $12–14 |
| NAT gateway / static egress IP | $32 |
| Egress, 200 GB / month | $18–22 |
| Logs and monitoring, 20 GB / month | $10–14 |
| Container registry | $5 |
| Fixed subtotal | $262–302 |

### Per-unit service rates

| Service | Rate |
| --- | --- |
| Document OCR | $1.50 per 1,000 pages (Textract) |
| Speech-to-text | $1.44 per audio hour (Transcribe) |
| Legal search fallback | ≈ $810 / month (Kendra) or ≈ $125 (self-built OpenSearch) |
| Embeddings | $0.02 per 1M tokens (Titan v2) |
| Flagship model (Opus tier) † | $5.00 / $25.00 per 1M tokens in / out |
| Economy model (Sonnet tier) † | $2.00 / $10.00 per 1M tokens in / out |

† Placeholder model rates; verify model names, prices and regional availability with the provider.

### Worked monthly total

Modelled at 15,000 OCR pages, 50 audio hours, 3,000 search queries, 50M embedding tokens and 300M input / 40M output model tokens a month (≈ 500 active workspaces). "Mixed" puts 30% of tokens on the flagship model (strategy, analysis report, drafting) and 70% on the economy model — made possible by per-feature model selection.

| Cost line | With OpenSearch | With Kendra |
| --- | --- | --- |
| Fixed infrastructure | $285 | $285 |
| OCR (15,000 pages) | $23 | $23 |
| Transcription (50 hours) | $72 | $72 |
| Legal search | $125 | $810 |
| Embeddings (50M tokens) | $1 | $1 |
| Models — economy everywhere | $1,000 | $1,000 |
| Models — mixed (flagship on reasoning panels) | $1,450 | $1,450 |
| Models — flagship everywhere | $2,500 | $2,500 |
| Monthly total — economy | ≈ $1,506 | ≈ $2,191 |
| Monthly total — mixed (recommended) | ≈ $1,956 | ≈ $2,641 |
| Monthly total — flagship | ≈ $3,006 | ≈ $3,691 |

AWS Business Support: 10% of monthly spend, $100 minimum. Indicative USD list prices, Mumbai region, before commitments, discounts and taxes.

## 4.7 AWS-specific risks

| ID | Risk | Mitigation |
| --- | --- | --- |
| R-A1 | Download links expire. S3 presigned links last at most 7 days (less under an IAM role); draft documents are currently shared as long-lived links. | Redirect endpoint that mints a fresh link per click (A-08). Changes what the backend stores — backend sign-off needed in week 1. |
| R-A2 | No native web grounding. Case-law discovery through web search must be built. | Phase 2 (P2-A1). Case laws keep working in phase 1 through direct Indian Kanoon lookup. |
| R-A3 | OS ownership on EC2. The instance must be patched and monitored. | Systems Manager patch baseline and maintenance window; CloudWatch agent; Auto Scaling group of one for recovery. |
| R-A4 | Bedrock model access and quotas in Mumbai must be granted before week 2. | Request on day 1; the portability layer allows a fallback model per feature if a quota is short. |
| R-A5 | Kendra is priced per provisioned hour (≈ $810 / month floor). | Phase 1 builds self-managed OpenSearch (≈ $125 / month, A-16); Kendra is considered only if real query volume justifies it. |

# 5. Work plan — Microsoft Azure

Everything needed to run SimplerToday AI fully on Azure. Phase 1 delivers a production cutover in 4 weeks; phase 2 completes the remaining capabilities and full quality parity.

## 5.1 Service mapping

| Capability | Azure service | Notes |
| --- | --- | --- |
| Always-on AI service | Azure Container Apps, min = max = 1 replica | Single instance only — one connection to the backend |
| Vector store | Qdrant on an Azure VM with a managed disk (or Qdrant Cloud) | Snapshot and restore verified |
| Cache | Azure Cache for Redis (small) | Provisioned for continuity |
| Draft documents, templates, audio staging | Blob Storage with long-lived SAS download links | Matches current link behaviour |
| OCR for scanned evidence | Azure AI Document Intelligence | Benchmark on Indian court filings |
| Audio transcription + speaker separation | Azure AI Speech (batch transcription) | Benchmark Hindi–English audio |
| Language model | Azure OpenAI (flagship for reasoning panels, economy for the rest) | Through the portability layer |
| Embedding model | text-embedding-3-small (1,536-dim) | Vector store re-built from stored text |
| Web grounding for case law | Grounding with Bing Search | Phase 1 |
| Legal search fallback | Azure AI Search (Basic) + crawler | Phase 1 |
| Secrets and identity | Key Vault + Managed Identity | Old key files rotated and revoked |
| Logs, metrics, alarms | Log Analytics + Azure Monitor | Audit trail preserved |

## 5.2 Work breakdown — phase 1

| ID | Task | Owner | Days | Depends on |
| --- | --- | --- | --- | --- |
| Z-01 | Portability integration — existing client methods re-pointed at the portability layer; per-feature model selection; five direct SDK calls moved; embedding size check; per-model pricing; tests | E1 | 4–5 | — |
| Z-02 | Subscription, resource groups, VNet, NAT gateway with static public IP, budget alerts | E2 | 2 | Client: subscription |
| Z-03 | Container image with ffmpeg and poppler; Azure Container Registry; Container Apps environment pinned to one replica; CI pipeline | E2 | 2 | Z-02 |
| Z-04 | Qdrant on a VM with managed disk; snapshot, restore and verify; Azure Cache for Redis | E2 | 2 | Z-02 |
| Z-05 | Key Vault, Managed Identity; rotate and revoke existing key files | E2 | 2 | Z-02 |
| Z-06 | Log Analytics and Azure Monitor alerts (socket disconnect, restarts); audit-log retention | E2 | 1 | Z-03 |
| Z-07 | Data migration to Blob Storage; backfill stored storage references in cached templates | E2 | 2 | Z-08 |
| Z-08 | Blob storage adapter with long-lived SAS download links | E3 | 2 | Z-02 |
| Z-09 | Document Intelligence OCR adapter; flatten output to the text the pipeline expects; benchmark | E3 | 2 | Sample evidence |
| Z-10 | AI Speech batch adapter with speaker separation; reproduce the [MM:SS] Speaker A: format; Hindi–English test | E3 | 4 | Sample evidence |
| Z-11 | Azure OpenAI embeddings; re-embed the vector store from stored text; retrieval-quality check | E1 | 1 | Z-01, Z-04 |
| Z-12 | Golden set (10 anonymised cases with lawyer-approved outputs) and automated scorer | E3 | 3 | Client: cases |
| Z-13 | Prompt tuning on Azure OpenAI for all ten panels and chat until output is valid and meets the golden-set threshold; remaining polish continues in phase 2 | E1 + E3 | 7 | Z-01, Z-12 |
| Z-14 | Content-filter configuration (after approval) on real evidence; cost tracking for Document Intelligence, Speech and Azure OpenAI units | E1 | 2 | Approval |
| Z-15 | Grounding with Bing Search for case-law discovery | E1 | 2 | Z-01 |
| Z-16 | End-to-end regression on staging, parallel run, cutover, rollback rehearsal, runbooks, handover | All | 4 | All above |
| Z-17 | Legal search fallback — crawler indexing Indian Kanoon into Azure AI Search (Basic); query adapter returning passages and source links | E2 | 3 | Z-02 |
|  | Phase 1 total |  | 45–46 |  |

E1 = AI engineer · E2 = cloud / DevOps engineer · E3 = backend & QA engineer (section 7).

## 5.3 Week-by-week plan — phase 1

| Week | E1 — AI engineer | E2 — cloud / DevOps | E3 — backend & QA |
| --- | --- | --- | --- |
| Week 1 | Z-01 portability integration; service runs through the layer with no behaviour change. Submit the Azure OpenAI modified content-filter application and quota request. | Z-02 foundation; Z-03 container and CI; Z-05 Key Vault and key rotation. | Z-08 Blob adapter with SAS links; start Z-12 golden set. |
| Week 2 | Azure OpenAI profiles live in the layer; Z-11 embeddings and re-embed dry run; Z-13 tuning starts (strategy, analysis report). | Z-04 Qdrant and cache; Z-06 observability; Z-07 data migration to staging. | Z-09 Document Intelligence; Z-10 AI Speech; Z-12 golden set complete. |
| Week 3 | Z-13 tuning remaining panels and chat; Z-15 Bing grounding; Z-14 content filter and cost tracking. | Z-17 legal search (crawler + AI Search); full staging deployment end to end; alerts; draft runbook. | Z-13 tuning support (dates, parties, laws, drafting); golden-set scoring; OCR / transcription benchmark on real evidence. |
| Week 4 | Fixes from regression; final golden-set score. | Parallel run; IP allowlisting; cutover; rollback rehearsal. | Z-16 full regression across every event, panel and file type; handover. |

## 5.4 Milestones and gates

| Gate | When | Pass criteria |
| --- | --- | --- |
| G0 · Start | Day 1–3 | Azure account with admin rights, model access requested, staging backend available, sample evidence and 10 golden-set cases received |
| G1 · Layer in place | End of week 1 | Service runs through the portability layer with no behaviour change; existing offline verification scripts pass; foundation network and secrets ready |
| G2 · Target reachable | End of week 2 | Azure models reachable through the layer; data migrated to staging; golden set and scorer ready |
| G3 · Staging complete | End of week 3 | All panels and chat return valid output on the target model; golden-set score at or above threshold; legal search fallback returns Indian Kanoon results; staging end-to-end run clean |
| G4 · Go / no-go | Week 4 | Regression passed, rollback rehearsed, backend team sign-off on the cutover window |

## 5.5 Phase 2 — after cutover

| ID | Task | Days |
| --- | --- | --- |
| P2-Z1 | Golden set extended to 25–30 cases; prompt polish to full parity | 11–15 |
|  | Phase 2 total | 11–15 |

Phase 2 runs over 2–3 weeks with 1–2 engineers.

## 5.6 Running cost

### Fixed monthly infrastructure

| Line item | Azure |
| --- | --- |
| Application container, 2 vCPU / 8 GB, always on | $75–90 (VM) · ≈ $180 (Container Apps) |
| Qdrant, 2 vCPU / 8 GB + 100 GB disk | $85–105 |
| Redis cache, small | $16–40 |
| Object storage, 500 GB | $10–13 |
| NAT gateway / static egress IP | $32 |
| Egress, 200 GB / month | $15–18 |
| Logs and monitoring, 20 GB / month | $40–50 |
| Container registry | $5 |
| Fixed subtotal | $278–353 |

### Per-unit service rates

| Service | Rate |
| --- | --- |
| Document OCR | $1.50 per 1,000 pages (Document Intelligence) |
| Speech-to-text | $1.00 per audio hour (AI Speech) |
| Legal search fallback | ≈ $75 / month fixed (AI Search Basic + crawler) |
| Web grounding | Grounding with Bing Search, per transaction |
| Embeddings | $0.02 per 1M tokens |
| Flagship model † | $4.00 / $20.00 per 1M tokens in / out |
| Economy model † | $2.00 / $12.00 per 1M tokens in / out |

† Placeholder model rates; verify model names, prices and regional availability with the provider.

### Worked monthly total

Modelled at 15,000 OCR pages, 50 audio hours, 3,000 search queries, 50M embedding tokens and 300M input / 40M output model tokens a month (≈ 500 active workspaces). "Mixed" puts 30% of tokens on the flagship model (strategy, analysis report, drafting) and 70% on the economy model — made possible by per-feature model selection.

| Cost line | Monthly |
| --- | --- |
| Fixed infrastructure | $310 |
| OCR (15,000 pages) | $23 |
| Transcription (50 hours) | $50 |
| Legal search | $75 |
| Embeddings (50M tokens) | $1 |
| Models — economy everywhere | $1,080 |
| Models — mixed (flagship on reasoning panels) | $1,356 |
| Models — flagship everywhere | $2,000 |
| Monthly total — economy | ≈ $1,539 |
| Monthly total — mixed (recommended) | ≈ $1,815 |
| Monthly total — flagship | ≈ $2,459 |

Azure Standard Support: about $100 / month. Indicative USD list prices, Mumbai region, before commitments, discounts and taxes.

## 5.7 Azure-specific risks

| ID | Risk | Mitigation |
| --- | --- | --- |
| R-Z1 | Content-filter approval lead time. Default Azure OpenAI filters block normal legal evidence (allegations, violence, medical detail); relaxed filtering needs an approved application. | Apply on day 1. If approval is late, the portability layer keeps affected features on an approved model until it lands. |
| R-Z2 | Log Analytics ingestion cost is about four times the other clouds' for the same volume. | Retention and sampling policy set in Z-06; review after the first month. |
| R-Z3 | Azure OpenAI model availability and quotas in the chosen region. | Confirm on day 1; request quota increases before week 2. |
| R-Z4 | Azure AI Search has no built-in web crawler. | A crawler indexing Indian Kanoon into AI Search is built in phase 1 (Z-17). |

# 6. AWS, Azure and GCP compared

## 6.1 AWS and Azure side by side

| Topic | AWS (EC2) | Azure |
| --- | --- | --- |
| Phase 1 effort / calendar | 45–46 days · 4 weeks | 45–46 days · 4 weeks |
| Phase 2 effort / calendar | 15–21 days · 2–3 weeks | 11–15 days · 2–3 weeks |
| Total programme | 60–67 days | 56–61 days |
| Compute | EC2 + Auto Scaling group of one; team owns OS patching | Container Apps pinned to one replica; managed platform |
| Download links | Redirect endpoint (backend change) | Long-lived SAS links (no change) |
| Web grounding | Built in phase 2 | Bing grounding in phase 1 |
| Legal search fallback | OpenSearch in phase 1 (≈ $125 / mo); Kendra optional (≈ $810 / mo) | AI Search Basic in phase 1 (≈ $75 / mo) |
| Main approval to chase | Bedrock model access and quotas | Azure OpenAI content-filter application and quotas |
| Fixed infrastructure / month | $262–302 | $278–353 |
| Monthly total — mixed models | ≈ $1,956 (OpenSearch) · ≈ $2,641 (Kendra) | ≈ $1,815 |
| Monthly total — flagship everywhere | ≈ $3,006 · ≈ $3,691 | ≈ $2,459 |
| Support plan | 10% of spend, $100 minimum | ≈ $100 / month |

## 6.2 Running-cost comparison including GCP

For a clear view of the running cost, the tables below put both target clouds next to Google Cloud (GCP) running the same workload on Gemini through Vertex AI. Same modelled volume as sections 4.6 and 5.6: 15,000 OCR pages, 50 audio hours, 3,000 search queries, 50M embedding tokens and 300M input / 40M output model tokens a month.

### Fixed monthly infrastructure

| Line item | GCP | Azure | AWS (EC2) |
| --- | --- | --- | --- |
| Application server / container, 2 vCPU / 8 GB | $50–70 | $75–90 (VM) · ≈ $180 (Container Apps) | $75–85 |
| Qdrant, 2 vCPU / 8 GB + 100 GB disk | $60–85 | $85–105 | $85–100 |
| Redis cache, small | $15–25 | $16–40 | $25–30 |
| Object storage, 500 GB | $10–13 | $10–13 | $12–14 |
| NAT gateway / static egress IP | $32 | $32 | $32 |
| Egress, 200 GB / month | $20–24 | $15–18 | $18–22 |
| Logs and monitoring, 20 GB / month | $8–12 | $40–50 | $10–14 |
| Container registry | $5 | $5 | $5 |
| Fixed subtotal | $200–266 | $278–353 | $262–302 |

### Per-unit service rates

| Service | GCP | Azure | AWS |
| --- | --- | --- | --- |
| Document OCR, per 1,000 pages | $1.50 (Vision) | $1.50 (Document Intelligence) | $1.50 (Textract) |
| Speech-to-text, per audio hour | $0.96 (Chirp 3) | $1.00 (AI Speech) | $1.44 (Transcribe) |
| Legal search fallback | $1.50 / 1k queries (Vertex AI Search) | ≈ $75 / month fixed | ≈ $125 (OpenSearch) or ≈ $810 (Kendra) / month |
| Embeddings, per 1M tokens | $0.15 | $0.02 | $0.02 |
| Web grounding | Google Search grounding, $14 / 1k requests | Bing grounding, per transaction | Built (search API, per query) |
| Flagship model, per 1M tokens in / out † | $2.00 / $12.00 (Gemini Pro) | $4.00 / $20.00 | $5.00 / $25.00 (Claude Opus tier) |
| Economy model, per 1M tokens in / out † | $0.50 / $3.00 (Gemini Flash) | $2.00 / $12.00 | $2.00 / $10.00 (Claude Sonnet tier) |

† Placeholder rates; verify model names, prices and regional availability with each provider. Gemini Flash is priced at its preview rate, which may rise at general availability.

### Worked monthly total

| Cost line | GCP | Azure | AWS (OpenSearch) | AWS (Kendra) |
| --- | --- | --- | --- | --- |
| Fixed infrastructure | $230 | $310 | $285 | $285 |
| OCR | $23 | $23 | $23 | $23 |
| Transcription | $48 | $50 | $72 | $72 |
| Legal search | $5 | $75 | $125 | $810 |
| Embeddings | $8 | $1 | $1 | $1 |
| Models — economy everywhere | $270 | $1,080 | $1,000 | $1,000 |
| Models — mixed (recommended) | $513 | $1,356 | $1,450 | $1,450 |
| Models — flagship everywhere | $1,080 | $2,000 | $2,500 | $2,500 |
| Monthly total — economy | ≈ $584 | ≈ $1,539 | ≈ $1,506 | ≈ $2,191 |
| Monthly total — mixed (recommended) | ≈ $827 | ≈ $1,815 | ≈ $1,956 | ≈ $2,641 |
| Monthly total — flagship | ≈ $1,394 | ≈ $2,459 | ≈ $3,006 | ≈ $3,691 |

Mixed = 30% of model tokens on the flagship (strategy, analysis report, drafting), 70% on the economy model. Indicative USD list prices, Mumbai region, before commitments, discounts, support plans and taxes.

### Annual view — mixed model profile

|  | GCP | Azure | AWS (OpenSearch) | AWS (Kendra) |
| --- | --- | --- | --- | --- |
| Monthly | ≈ $827 | ≈ $1,815 | ≈ $1,956 | ≈ $2,641 |
| Annual | ≈ $9,900 | ≈ $21,800 | ≈ $23,500 | ≈ $31,700 |
| Difference vs GCP, per year | — | + ≈ $11,900 | + ≈ $13,500 | + ≈ $21,800 |

### What drives the difference

- Model token rates are almost the whole gap. Infrastructure, OCR, transcription and embeddings are within about $100 a month of each other on all three clouds; the language-model line is where GCP is cheaper, because Gemini is priced well below the equivalent Azure OpenAI and Claude tiers.

- Legal search is the other swing factor on AWS: Kendra's provisioned floor adds about $685 a month over a self-built OpenSearch index.

- Per-feature model selection narrows the gap on every cloud — the mixed profile is roughly 25–35% cheaper than flagship everywhere on Azure and AWS.

- GCP figures are the least firm for the economy model, which is on preview pricing and more likely to rise than fall.

- One-time effort is separate from running cost: moving to AWS or Azure is the programme in sections 4 and 5; the model portability integration (4–5 days) applies on any cloud, including GCP.

# 7. Team and governance

## 7.1 Team

| Role | Responsibilities | Allocation |
| --- | --- | --- |
| E1 — AI engineer | Portability integration, embeddings and re-embed, prompt tuning, safety posture, grounding | Full time, weeks 1–4 |
| E2 — Backend & QA engineer | Storage, OCR and transcription adapters, golden set and scorer, prompt tuning support, regression | Full time, weeks 1–4 |
| Technical lead (part time) | Plan, gate reviews, backend-team coordination, client reporting | ≈ 20% |

## 7.2 Calendar by team size

| Team |  |
| --- | --- |
| One engineer | 4 weeks |

# 8. Quality, testing and acceptance

## 8.1 How quality is proven

- Golden set: 10 anonymised cases in phase 1 (25–30 in phase 2), each with lawyer-approved outputs for every panel.

- Automated scorer: checks every panel for valid structure and scores its content against the approved outputs.

- Existing verification scripts for workspace flows (document reload, objective change, sharing, fact corrections, stop/resume) run on every build.

- Benchmarks for OCR and transcription on the client's real evidence, including scanned court filings and Hindi–English audio.

- End-to-end regression across every socket event, all ten panels, chat, sharing, objective change, document deletion, workspace purge and every supported file type.

## 8.2 Go / no-go criteria for cutover

| Criterion | Threshold (to be agreed) |
| --- | --- |
| Every panel and chat returns valid output on every golden-set case | 100% |
| Golden-set content score (lawyer-approved outputs) | ≥ agreed threshold, e.g. 90% |
| Outputs blocked by content filters on golden-set evidence | 0 |
| OCR and transcription within agreed tolerance on the benchmark set | Pass |
| Existing verification scripts | All pass |
| Cost and usage metadata reported on every response | Pass |
| Rollback rehearsed on staging | Done |

# 9. Cutover and rollback

## 9.1 Cutover steps

- Freeze deployments on the current environment; announce the window to the backend team.

- Final data sync: object storage delta, stored-reference backfill, vector store re-embed (or restore of the pre-built collection).

- Deploy the release to the target cloud; confirm the outbound IP is allowlisted by the backend.

- Stop the current service first, then start the new one — two connected instances would duplicate responses.

- Smoke test on production: create a workspace, receive all panels, chat, upload and delete a document.

- Monitor for 24–48 hours: socket connection, error rate, panel completion, cost metadata.

## 9.2 Rollback

- The previous environment stays warm for 2–4 weeks after cutover.

- Rollback is stop-new, start-old; the portability layer can also route individual features back to a previous model by configuration.

- Workspace state written after cutover lives in the new vector store; the rollback runbook includes re-syncing it to the old environment.

- Rollback trigger: any go/no-go criterion failing in production, agreed with the client in advance.

# 10. Assumptions and exclusions

## Assumptions

- A team of three engineers is available full time for phase 1.

- The model portability layer already exists and supports the capabilities in section 3.3.

- Only the AI service moves; the application backend stays where it is.

- Client inputs (account, model access, staging backend, sample evidence and golden-set cases) arrive in the first three days; each week of delay moves the end date by a week.

- Feature development on the affected modules is frozen for the 4 weeks.

- Volumes in the cost sections are modelled, not measured.

- Model names, prices, regional availability and quotas are confirmed with the providers.

## Not included

- High availability, multi-region or active/active deployment.

- Changes to product behaviour or feature scope.

- Migration of the vendored Keel knowledge-plane copy.

- Firm infrastructure or model pricing.

## One-time costs to budget

- Engineering effort: phase 1 and phase 2 days multiplied by the agreed day rate.

- Dual running for the 4-week migration and a 2–4 week rollback window.

- One-time data transfer of about 500 GB (≈ $60).

- Vector store re-embed — a few dollars of embedding cost.

SimplerToday AI — migration work plan, AWS and Azure · v4.0 · 30 September 2026. Effort in engineering person-days, excluding client-side approvals and provisioning. Costs are indicative USD list prices for the Mumbai region.